## RACI
RACI MATRIX Responsible & Task | 1.1.1. Define project objectives | 1.1.2. Define project scope | 1.1.3. Define success criteria | 1.2.1. Determine project feasibility | 1.2.2. Define tradeoffs (accuracy, speed, explainability) | 1.3.1. Design the solution | 1.3.2. Define required infrastructure | 2.1.1. Ingest Data | 2.1.2. Data cleansing | 2.2.1. Edit metadata | 2.2.2. Aggregate data | 2.2.3. Transform data | 2.3.1. Install/ Configure required technical components | 3.1.1. Extract features | 3.2.1. Develop/ Adapt prediction model | 3.3.1. Run POC | 3.4.1. Train model | 3.4.2. Score Model | 3.4.3. Evaluate Model | 4.1.1. Obtain Acceptance | 4.1.2. Deploy model | 4.2.1. Maintain model
CEO | R,A | C | C | I | I | [14 empty] | A
Marketing Director | C | C | C | I | I | [14 empty] | A
Project Manager | I | R,A | R | R,A | R,A | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R
IT Director | C | C | C | R | R | A | R | [12 empty] | A
Dev Lead |  | I | I |  |  | I | [9 empty] | R,A
Database Specialist |  | I | I |  |  | I | C | C |  |  |  |  | R | [7 empty] | R,A
IT Infrastructure Specialist | [12 empty] | R,A
IT Developer |  | I | I |  |  | I | [6 empty] | I | [7 empty] | R
Data Scientist | C | C | C | R | R | R,A | C | R | I | R | R | R | I | R | R,A | R | R,A | R,A | R,A | A | I | R,A
Solution Architect |  | I | C | R | R | R,A | R,A | C | C |  |  |  | I |  |  | R |  |  |  | C | C
Data Architect |  | I | I | R | R | I | C | R | R | R | R | R | I | R | R | R | R | R | R | C | R
Data Engineer | [9 empty] | R | R | R | I | R | R | R | R | R | R |  | R | bar: I C I to I R R; I R,A R,A; I R C to I I C
Data Viz Engineer |  | I | I | R |  | I |  |  | C |  | C |  | I | C | C | R | C | C | C
Data Analyst |  | I | I | R |  | I |  | C | R | R | R | R | I | R |  | R | R | R | R
Business Analyst |  | I | I | R |  | I |  | C |  |  | C |  | I |  |  | R | C | C | C | C
Data Extraction Specialist |  | I | I |  |  | I |  | R,A | R,A | R,A |  |  | I
QA Specialist | [12 empty] | I |  |  |  |  | R | R | bar: I C I to I C C; I R,A R,A
Machine Learning Eng. |  | I | I | R |  | I | C | C | I | I | R,A | R,A | I | R,A | R | R | R | R | R | I | C | R

## WBS
WORK BREAKDOWN STRUCTURE
PROJECT TITLE | Montreal Fire Department Optimization | COMPANY NAME | Montreal Fire Dept
PROJECT MANAGER | Marshmello Team | DATE | 2019-03-08
Montreal Fire Department Optimization
1. Ideation
Project Setup
Feasibility Analysis
Solution Architecture
1.1.1. Define project objectives
1.1.2. Define project scope
1.1.3. Define success criteria
1.2.1. Determine project feasibility
1.2.2. Define tradeoffs
1.3.1. Design the solution
1.3.2. Define required infrastructure
2. Preparation
Data Ingestion
Data Preparation
Infrastructure Setup
2.1.1. Ingest Data
2.1.2. Data cleansing
2.2.1. Edit metadata
2.2.2. Aggregate data
2.2.3. Transform data
2.3.1. Install/ Configure required technical components
3. Prototyping and Testing
Feature Engineering
Modeling and Development
PoC
3.1.1. Extract features
3.2.1. Develop/ Adapt prediction model
3.3.1. Run POC
4 Productization
Train/Test/ Evaluate
Deployment
Operation
3.4.1. Train model
3.4.2. Score Model
3.4.3. Evaluate Model
4.1.1. Obtain Acceptance
4.1.2. Deploy model
4.2.1. Maintain model